## TestPlan
Date Found | Version Number | Test Platform | Description of Problem | Date Fixed | Action Taken
2014-03-24 | 0.6 | Windows PC | Ufos and their bullets would appear on main menu | 2014-03-24 | Created a stopListening() command in appropriate classes
2014-03-25 | 0.61 | Mac Laptop | Photoshop Image won't allow layers to be menu items | 2014-03-25 | Created multiple images instead of one layered image
2014-03-25 | 0.7 | Mac Laptop | Bonus lives functionality added | 2014-03-25 | Created a bonusLives function in friendlyPlane class and a variable in main game to handle appropriate handling of bonus lives
2014-03-25 | 0.71 | Mac Laptop | Bonus functionality not working as planned | 2014-03-25 | Missed adding points to bonus when a bullet hit a bullet.
2014-03-25 | 0.72 | Mac Laptop | Bonus lifes increasing, but damaged plane remains | 2014-03-25 | Added the call to change alpha value in the bonusLife() method.
2014-03-25 | 0.75 | Mac Laptop | Ufos shoot too many bullets | 2014-03-25 | Changed the random value for the ufo class to be higher, making on average a longer waiting time till next bullet is shot
2014-03-25 | 0.75 | Mac Laptop | Ufo bullets do not disappear, instead go blurry | 2014-03-25 | Changed the value from 800 to 700 when removing ufo bullets from the stage, works perfectly!
2014-03-25 | 0.75 | Mac Laptop | Animated bullets not animating | 2014-03-27 | Found that they are animating correctly, just not noticeable on screen as they are too small
2014-03-25 | 0.75 | Mac Laptop | Explosion not appearing when homeplane is hit | 2014-03-25 | Changed checkForCollisions method so explosion is added in position of homeplane rather than the movieclip in the if statement
2014-03-25 | 0.8 | Mac Laptop | Ufos frequently go offscreen | 2014-03-27 | Inadvertently fixed when creating vertical movement for ufos
2014-03-25 | 0.8 | Mac Laptop | Ufo movement has to be better i.e move vertically | 2014-03-27 | Vertical movement added in ufo code, similar to horizontal movement
2014-03-26 | 0.8 | Mac Laptop | Bonus wouldn't reward until over 100 | 2014-03-26 | Changed the if (bonusNeeded > 100) to if (bonusNeeded >= 100)
2014-03-26 | 0.8 | Mac Laptop | Ship when hit goes alpha, could be better | 2014-03-27 | Graphics created in friendlyplane timeline with stops. Used code like 'if (this.currentFrame == 6) gotoAndStop(1);' in the classmethods isHit() and bonusLife() to change the frame of plane
2014-03-27 | 0.8 | Mac Laptop | Ufos shoot on spawn | 2014-03-27 | Added a delay to ufo shooting on spawn
2014-03-29 | 0.8 | Mac Laptop | Spawn delay of new ufos is too long | 2014-03-29 | Halved the delay to 50 in the actions main part of the program
2014-03-29 | 0.8 | Mac Laptop | UfoCount deducts too many if our bullet hits the explosion | 2014-03-29 | Unsure why this suddenly came up as a problem, as none of the code was touched. Anyway, inserted an if statement to check whether the current ufoCount variable was positive before removing one
2014-03-29 | 0.8 | Mac Laptop | Too many ufobosses spawning when only one is supposed to | 2014-03-29 | Made a similar fix to that above - changed ufoBossCount details when removing from stage
2014-03-29 | 0.8 | Mac Laptop | Ufoboss bullets shoot the wrong way | 2014-03-29 | Changed the x direction within the ufobossbullet class
2014-03-29 | 0.8 | Mac Laptop | Menu design wasn't attractive as I'd like | 2014-03-29 | Brought the main menu image in line in quality and consistency with the insturctions page
2014-03-29 | 0.8 | Mac Laptop | Ufobullet should be animated, it's the only one that isnt.. It will also help with coupling the ufobullet and ufobossbullet hit detection on the ship into one method | 2014-03-29 | Ufobullet now animated, also had to change the size of bullet during creation as it was too big at 30 x 30 pixels
2014-03-29 | 0.8 | Mac Laptop | Scrolling background would be AWESOME! | 2014-03-29 | Added, took a while to understand how to create a seamless animation but game now has one.
2014-03-29 | 0.9 | Mac Laptop | In the rare occasion 500 points are scored and no ufos left, user is stuck. | 2014-03-29 | Changed the if statement for where a ufoboss spawns for less than or equal to 500 points when spawning
2014-03-29 | 0.9 | Mac Laptop | Explosion animations happening more than once for ufoboss and ufos | 2014-03-29 | Added two if statements that check the current frame of the hit ufo/ufoboss before calling the statements of being hit
2014-03-29 | 0.9 | Mac Laptop | Game feels too black and white, needs more colour | 2014-03-29 | Changed the background of the first level to include more colour and be more vibrant. Added new graphics in the background like a spaceship, astronaut and satellite to make map feel more alive.
2014-03-29 | 0.9 | Mac Laptop | Buttons not perfect, had a section erased | 2014-03-29 | Fixed by adding new layer in photoshop to fix erased area
2014-03-29 | 0.9 | Mac Laptop | Results panel doesn't play when game ends, instead hops to last frame | 2014-03-31 | Results panel now plays with addition of new actionscript code
2014-03-29 | 0.9 | Mac Laptop | Transition to instructions fades to the old screenshot | 2014-03-29 | Replaced the old screenshot with a new one of the new interface
2014-03-29 | 0.9 | Mac Laptop | Ufoboss should shoot quicker | 2014-03-29 | Updated the ufoboss shooting values to be quicker
2014-03-31 | 0.9 | Windows PC | Bullets would look nicer with a shadow backdrop on background | 2014-03-31 | Individual parts of the ufobullet gif have had a shadow addd via photoshop
2014-03-31 | 0.9 | Windows PC | Rank number and hall of fame title along the highscores would be cool | 2014-03-31 | New graphics added to highscore area
2014-03-31 | 0.9 | Mac Laptop | Friendly bullets animation isn't visible in game | 2014-04-01 | Updated friendly bullets to a new graphic
2014-04-02 | 0.9 | Windows PC | Ship doesn't move gradually across screen when boss is beaten | 2014-04-02 | Added tween code to make plane move gradually
2014-04-02 | 0.9 | Windows PC | Movement of ship should be smoother | 2014-04-03 | Changed movement code to a variable, much like Pong game controls from earlier practical
2014-04-02 | 0.9 | Windows PC | Reset button and home button on instrcutions page doesn't work | 2014-04-02 | Made a new call in the main game to reset variables to original values and also named the movieclip screens to have a name and make them visible. This helped greatly to make the functions
2014-04-03 | 1 | Mac Laptop | Would be nice to have graphic to illustrate lives than a number | 2014-04-03 | Added a similar system to the change of graphics for the friendlyship
2014-04-03 | 1 | Mac Laptop | When ufoboss dies, his bullets remain there so during the animation of player completing the level, it forces the player to lose a life | 2014-04-03 | Added a more detailed cleanUp() routine to check if the boss has been defeated for the ufoboss bullets to removed from the stage
2014-04-03 | 1 | Mac Laptop | Ufoboss spawns too quick | 2014-04-03 | Added similar interval code for the ufo spawning for the bosses. Means I can toggle how long a wait should be before a boss spawns
2014-04-03 | 1 | Mac Laptop | Main menu could have a direct link to the highscores | 2014-04-03 | Created a highScore() method in main timeline, which is called when the highscore option is clicked in the splashScreen
2014-04-03 | 1 | Mac Laptop | Animation needs to be updated for main menu to include highscore option now | 2014-04-04 | Animation for splashScreen fixed to include the fade to black for the highscore menu option
2014-04-06 | 1 | Mac Laptop | Ufos and boss should be different for second level | 2014-04-06 | New symbols created for 2nd level boss and 2nd level normal ufos
2014-04-06 | 1 | Mac Laptop | New technique for boss should be implemented | 2014-04-06 | Boss has a special box vulnerability. He provides player with a collectible which can be used to shoot a special bullet at the boss. This bullet is the only one that damages the boss.
2014-04-06 | 1 | Mac Laptop | New technique for normal enemy shooting should be implemented | 2014-04-06 | Added a triple shooting ufo for the second level
2014-04-06 | 1 | Mac Laptop | Instructions should appear for player if they try and kill boss with normal bullets | 2014-04-06 | Created a graphic/symbol in photoshop. This now appears onstage whenever the player tries to shoot the boss with normal bullets and provides instructions on what control to use to kill boss.
2014-04-06 | 1 | Mac Laptop | Position of special bullet relies upon position of ship. Doesn't take up full screen as intended. | 2014-04-06 | Made changes to the main actionscript so the position of the specialbullet from the friendlyplane is fixed to the stage rather than the position of the ship. This ensures a bullet that covers the screen as intended.
2014-04-06 | 1 | Mac Laptop | New graphics for bullets for the second level characters needs to be created | 2014-04-06 | New graphics created for the boss of the second level as well as the usual ufos.
2014-04-06 | 1 | Mac Laptop | Scoring system is hard to manage in current code | 2014-04-06 | Now managed by variables, it makes it much easier to have one location to change the values to make the game more fun and provide a consistent scoring experience.
2014-04-06 | 1 | Mac Laptop | Third level hasn't been created | 2014-04-06 | Created cave scrolling background,
2014-04-08 | 1 | Mac Laptop | Enemy characters sometimes spawn more than 3 characters | 2014-04-08 | Moved the if statement that removes 1 from the count
2014-04-08 | 1 | Mac Laptop | Levels functionality not added | 2014-04-08 | Levels graphics created and a new splashscreen function to handle it. Created reset code for each level so now each level completes correctly.
2014-04-08 | 1 | Mac Laptop | Cave background goes off screen, leaving white space for a map | 2014-04-08 | Beautiful animation of a larger image now resolves problem, map looks incredible.
2014-04-08 | 1 | Mac Laptop | Space Invaders black image blends in with background | 2014-04-08 | Changed colour of all space invaders to multicolours!
2014-04-09 | 1 | Mac Laptop | Space Invaders shoot too slow | 2014-04-09 | Changed the values of enemies so bullets shoot faster
2014-04-10 | 1 | Mac Laptop | No sounds in the game other than the explosions | 2014-04-10 | Different sounds added to the game for whenever something shootsand also added background track
2014-09-11 | 1.1 | Mac Laptop | Ship would be nice if it animated with a spin motion as it moves up and down on screen | 2014-09-11 | Part-way to fixing the problem by having functionality created for this animation. Just needs the graphics themselves to be created on photoshop and imported in place of the placeholder images
2014-09-11 | 1.1 | Mac Laptop | Would be nice to be able to pause the game | 2014-09-11 | Created functionality where the game can be paused with the 'p' key. Had a problem yesterday where unpausing was an issue. Turned out to be that when pausing, it removes event.enter_frane. Unpausing was a check to see if a sprite had this variable (that had just been removed!). So instead, I've created a individual check on seeing what the sprite is. If it's one of the ones that has the call to unpause (inside the code of the thing itself) then it runs this method.
2014-09-11 | 1.1 | Mac Laptop | Reloading would add an entire new dynamic to the game | 2014-09-16 | Reloading has been implemented with the 'r' key as the input. Created two variables, currentbullets and maxbullets. These can be used in the future to create a graphic much like how lives are represented on screen and also for upgrading when the user completes a level. On the 16th September, I finished the reloading splash image that appears when user keeps trying to shoot without reloading. Works a dream and doesn't flash all the time, only after the player has tried to shoot 5 or so bullets and flashes once till they try another 5 - very user friendly. Found one small bug where the reloadsplashticker wouldn't be reset when the player reloads as the popup was a thing handled by the user hitting shoot key too much. Now fixed by when user reloads, the counter resets too.
2014-09-11 | 1.1 | Mac Laptop | Pausing needs to have its own screen, with various options inside like returning to game easily, restarting the game they are on, muting sound and going back to menu | 2014-09-17 | Pause menu has been created with various options and buttons that now function! Going back to the game is easy and restarts the movement of all things on screen as you would expect as a player. Further options menu has been created that has a cool function that stops the music. An option to rage quit has been added which had problems as ufos etc would stay on screen as the cleanup() method wouldnt remove things as they wouldnt be in the right state. This meant creating a method that would literally take every piece of gameplay related things off screen no matter what, called cleanWipe().This is called whenever the user goes back to the homescreen.
2014-09-11 | 1.1 | Mac Laptop | Instructions for mario boss confusing to new players | 2014-09-11 | Reduced amount of text and included images to make it easier to understand the splash
2014-09-16 | 1.1 | Mac Laptop | The new pausemenu needs to have a frame it sets itself to so it can be removed from the scene automatically, as to avoid screwing up the checks of a load of procedures | 2014-09-18 | HUGE amount of bug fixes here. Made the pause menu appear on the correct layer, above all gameplay things. Pause menu has its own part in the game with functionality and clean up methods have been touched up and recreated in parts when the user rage quits for example. On 18th, added a reset menu part that confirms the player wants to restart
2014-09-17 | 1.2 | Mac Laptop | Create a version numbering system and backup system behind the scenes, much like how Minecraft is run. | 2014-09-17 | Created better management of backups and have a versioning system in place in the app that appears only in the main menu
2014-09-17 | 1.2 | Mac Laptop | Main menus age rating is unneccessary and out of place | 2014-09-17 | Changed the main menu image so it no longer has the pointless age rating
2014-09-18 | 1.2 | Mac Laptop | Timing of things would be a great add to the game. Like having a long time limit till the next reload a user can make, of which can then be upgraded in the upgrade menu to be shorter.. | 2014-09-18 | Reloading has its own timer which has been set with trial and error. Stops the shooting when reloading and has been assigned to a parameter setup where there is option for the speed of the reload to be increased with upgrades.
2014-10-12 | 1.3 | Mac Laptop | User can't easily mute the sounds from game without playing first | 2014-10-12 | Added options to the main menu
2014-10-12 | 1.3 | Mac Laptop | Mute buttons need a tweak, muting the music only/muting the gameplay audio only/restarting the audio's | 2014-10-12 | A new option to mute all sounds has been added to the options menu, alongside the option that only mutes the music. This provides a professional approach to muting sounds, which can easily be unmuted again.
2014-12-16 | 1.3 | Mac Laptop | Layers of the instructions panel would prevent user from being able to click buttons | 2014-12-16 | Moved the whole homebutton layer up above Scoringpanel, ie all panels so it works whether or not there is a layer transition
2014-12-16 | 1.3 | Mac Laptop | The instructions panel on the main menu should have the tranport buttons only operate when they are on the first frame they are supposed to be on. Currently, user can mash one button and have effect go over and over | 2014-12-16 | Changed the code for instructions panel so buttons either way work properly. Fixes a problem where player could mash a button and have the effect repeat itself. Fixed by including a check on the currentframe.
Things I'd like to add if I had time
2014-03-27 | 0.8 | Windows PC | Would be nice to have keyboard buttons allowing transition between instructions pages | 2014-12-12 | Whether this is actually 'required' I don't know. The plan is to have it released on mobile devices particularly so this would only be a problem when released to the website. When that time comes, it will be a minor problem to solve.
2014-03-31 | 0.9 | Windows PC | Menu interface should have keyboard functionality | 2014-12-12 | Same as above really, not really a problem till it gets released on the web and even then its still usable and not that big of a problem, more work than its worth for now
2014-03-26 | 0.8 | Mac Laptop | Big, Complex error where ship sprite is hit where there is a transparent gap in the ship image | 2014-12-12 | Out of scope due to time restrictions. Instead to fix this partially, all graphics will have the majroity of their transparent areas trimmed. This has been fixed for the meanwhile with better trimmed sprites
2014-09-16 | 1.1 | Mac Laptop | Upgrades options when the user completes a level
2014-09-16 | 1.1 | Mac Laptop | Better tweaking when the user plays just one level. Need observation and user testing
2014-09-16 | 1.1 | Mac Laptop | Would be nice for the background to stop moving when the user pauses the game | 2014-12-12 | A cosmetic change that should really 'just be expected' by the gamer. When paused though, do they really care? Potentially more work than its worth but should look into it at some point
2014-09-17 | 1.1 | Mac Laptop | The upgrades menu needs to be creative and have empty star places that when the user touches this one long empty stars image thing, it adds a star. Only when the user clicks the confirm button, does the upgrade come into play…
2014-09-17 | 1.2 | Mac Laptop | Ship needs to move with rotation like it does in the bookmarked link I found.
2014-09-17 | 1.2 | Mac Laptop | Ship should bounce off the top and bottom of the map like it does in the same bookmark as above
2014-09-17 | 1.2 | Mac Laptop | Parameter setup should be very similar to the bookmark so upgrading is easy to code
2014-12-12 | 1.2 | Windows PC | Touchscreen controls need to start to be added to the game so in maybe 4 months or so the game can be released as an app | 2014-12-12 | The idea I have for this is to have the app not be able to rotate for now when the user holds their phone landscape (or whether the OS just handles it then its fine). On the right hand side of the game where the friendlyship is, the top half of that side will control the movement of the ship going up and the bottom right side control the ship moving down. The entire left side of the screen will be dedicated to shooting. How reloading will be handled I don't know quite yet and neither have I fully thought about how the player will be able to kill the mario boss with the bonus bullets. Overall, I like this idea because of its simplicity so definitely the way to go.
2014-12-12 | 1.2 | Windows PC | A transparent guide on the buttons to press whenever the user starts a new game should appear everytime. I'd like this to take over the full screen indicating the areas and what they do easily whilst going ever more transparent in a tween whilst it disappears after like 3 seconds
2014-12-12 | 1.2 | Windows PC | Maybe have a help option once the above two have been implemented where a simple imageis in the options menu that tells player how to control
2014-12-12 | 1.2 | Windows PC | Need to think about monetisation. | 2014-12-12 | Not the biggest concern really. The only decision I'm set on is to have the app free to build up more players than if it would be paid. From there, should I implement ads? Should I enable in app purchases? How would they work if I did?
2014-12-12 | 1.2 | Windows PC | Have a think about what should happen at the end of the game | 2014-12-12 | Should the game roll back to level 1 when the player completes level 3 and it gets harder, like more enemies/they're faster? Should I have never ending numbers of levels which would be quite easy to add (potential DLC).
| 1.2 | Windows PC | Should upgrades menu work off of a coin based system, where you earn X coins based on your performance? Or, should it work like a token system where you get X number of tokens when you beat the boss?
2014-12-16 | 1.2 | Mac Laptop
2014-12-16 | 1.2 | Mac Laptop | Eventually have a different options menu on the main menu compared to the pause menu.
Changes that were made on SAMSUNG that should be copied to what I'm sure is a later version maybe on 2TB

## Credits
Date Accessed | Description of Image | Thumbnail | Where its used | URL | Description of site
2014-03-25 | Apocalyptic Gif |  | Ending scene when player loses all lives | http://25.media.tumblr.com/fdd215ddde18bca8450f73c0c884120d/tumblr_n10f21YAG71rpj04no1_500.gif | Social Networking blogging platform
2014-03-03 | Small UFO |  | Easy enemy in game | http://www.heathersanimations.com/alien1.html | Animations website
2014-03-25 | Dark Space |  | Instructions Background | http://funlava.com/wp-content/uploads/2013/05/43356xji6yrqla3.jpg | Wallpapers blogging site
2014-03-25 | Warp Image |  | Instructions Page and Special Bullet | http://www.funnyjunk.com/channel/gfx/Rainbow+Background/xasbGkn | Community image website
2014-03-25 | Arrow Keys |  | Instructions Page | http://static.freepik.com/free-photo/arrow-keys-vectors_637061.jpg | Free photos for download
2014-03-25 | Spacebar |  | Instructions Page | http://www.wpclipart.com/computer/keyboard_keys/large_keys/computer_key_Space_bar.png | Clipart photos for wallpapers
2014-03-26 | Snakefangs |  | Plane (when player reaches 5 lives) | http://www.funwallz.com/image/snake-fangs-venom-poison-hd-wallpaper-103130.jpg | Wallpapers website for desktop computers
2014-03-29 | Ufoboss |  | Boss for level 1 | http://www.free-animated-pictures.com/ufo-gifs.html | Gif animations website
2014-03-29 | Ufobullet |  | Bullet shot by ufo | http://free-animations.co.uk/bullets_animated/bullet_8.html | Gif animations website
2014-03-30 | Space game |  | Background of first level | http://www.vickiwenderlich.com/2011/05/game-pack-space-flier/ | Tutorials website on how to make a game
2014-03-31 | Lightning |  | Bonus life popup screen | http://www.clker.com/cliparts/c/7/2/8/11949857691296011514lightning_icon_benji_par_01.svg.hi.png | Royalty free clipart
2014-03-31 | New animated bullet |  | Shoots from friendly plane | http://www.wilsoninfo.com/anibullets.htm | Free animated gifs
2014-04-01 | Forest Art |  | Background for second level | http://www.geekgirlpenpals.com/wp-content/uploads/2014/02/solar-system.jpg | Community pen pals website
2014-04-03 | Funny Alien |  | Forest Level Ufo | http://www.free-animated-pictures.com/ufo-alien-animatedpictures.html | Animated pictures website
2014-04-03 | Animated Bullet |  | Forest Level Ufo's Bullet | http://free-animations.co.uk/bullets_animated/bullet_4.html | Free animations website
2014-04-03 | Video Game Heart |  | Used to represent lives for the player | http://schadengirl.blogspot.co.uk/2014/02/party-wednesday-8-bit-valentines.html | Personal blog website
2014-04-06 | Mario coin |  | Used as a bullet for the 2nd boss | http://media.photobucket.com/user/bbdata/media/mario_coin.gif.html?filters[term]=mario%20coin&filters[primary]=images&sort=1&o=32 | Photo sharing website
2014-04-06 | Mario |  | 2nd boss | http://tf2.gamebanana.com/sprays/59939 | Gaming wiki website
2014-04-06 | Item block |  | Collectible vs second boss | http://fantendo.wikia.com/wiki/Luigi's_Twist_Land | Nintendo fanboy wiki
2014-04-06 | Warning Symbol |  | Appears when player tries to kill 2nd boss with normal bullet | http://www.picgifs.com/graphics/warning-sign/graphics-warning-sign-261406-820901/ | Gif and images website
2014-04-06 | Parallax game background |  | Appears in the third level of the game as a background | http://www.ludumdare.com/compo/author/benko/ | Blogging/archive website
2014-04-08 | Space Invaders characters |  | Each appear as an enemy in level 3 | http://logicalzero.com/gamby/resources/ | Gaming resources website
2014-04-08 | Space Invader Boss |  | Appears as boss in last level | http://download2.polytechnic.edu.na/pub4/sourceforge/a/as/asmprogramacion/Scratch%20-%20Space%20Invaders/Resources/ | Space Invader Games Resource Website

## SoundCredits
Date Accessed | Description of Sound | Where its used | URL | Description of site
2014-03-26 | Sound Effects Explosion | Anytime an enemy is hit by a friendly bullet | https://www.youtube.com/watch?v=XjOtGgxaX5g | Video sharing website
2014-04-10 | Pew sound effect | First ufos when a bullet is shot | https://www.youtube.com/watch?v=t_Xi13klex8 | Video sharing website
2014-04-10 | M16 burst sound effect | Second ufos when their 3 bullets are shot | https://www.youtube.com/watch?v=hiz1k6T4HaA | Video sharing website
2014-04-10 | Space Invaders Bullet | Third level of ufos when a bullet is shot | https://www.youtube.com/watch?v=y4AzuQT6lNI | Video sharing website
2014-04-10 | Cartoon sound effect | Third boss when a bullet is shot | https://www.youtube.com/watch?v=y9QWnhGHpME | Video sharing website
2014-04-10 | Super mario coin effect | 2nd boss when a normal bullet is shot | https://www.youtube.com/watch?v=RfkcI8dhfsQ | Video sharing website
2014-04-10 | Super mario item box sound effect | 2nd boss when a special bullet is shot | https://www.youtube.com/watch?v=Ciy2VrvLlhs | Video sharing website
2014-04-10 | Space blaster sound effect | 1st ufo boss when a bullet is shot | https://www.youtube.com/watch?v=HS0GwmQy5pI | Video sharing website
2014-04-10 | Party horn sound effect | When any boss dies | https://www.youtube.com/watch?v=l6dX7gjjx_o | Video sharing website
2014-04-10 | In fast motion | Background music for the game | https://www.youtube.com/watch?v=fBSw8_LJT9w | Video sharing website